## Slide 1
Project Status Report Presentation Example
PMO-style delivery update for stakeholder review
Objective: Provide a clear, professional example of a project status report presentation that communicates progress, delivery confidence, risks, budget position, and decisions required.
Generated by 秒搭

## Slide 2
秒搭 · Slide 1
Executive Summary
Overall project status: Amber
Delivery confidence remains moderate
Key scope items are progressing to plan
Timeline pressure sits around testing and sign-off
Primary focus this period: stabilise delivery and close open actions
Open with a concise summary in a typical UK PMO style. Explain that the project is currently rated Amber due to manageable but material delivery risks, rather than critical failure. Confirm that core workstreams are moving forward, but note pressure on the plan caused by testing readiness, stakeholder approvals, and dependency management.

## Slide 3
秒搭 · Slide 2
Progress Since Last Reporting Period
Requirements baseline approved by business lead
Core build completed for priority features
Data migration rehearsal finished with minor defects
Supplier weekly governance now in place
Training materials drafted for first user group
Use this slide to show tangible movement since the previous report. Keep commentary factual and specific. Highlight completed outputs, governance improvements, and any progress that reduces uncertainty. If presenting to senior stakeholders, focus on outcomes rather than detailed task activity.

## Slide 4
秒搭 · Slide 3
Milestone Tracker
Discovery and planning: Complete
Design sign-off: Complete
Build phase: On track
System integration testing: At risk by 1 week
User acceptance testing: Dependent on business availability
Walk through milestone status using clear stage language. Emphasise where dates remain secure and where slippage risk exists. For the at-risk items, explain the cause and current mitigation. This is a useful slide for sponsors who want visibility of critical path movement without reviewing the full project plan.

## Slide 5
秒搭 · Slide 4
Budget and Resource Position
Approved budget: £850k
Actual spend to date: £510k
Forecast at completion: £872k
Variance forecast: +£22k
Main pressure: extended test support and contractor cover
Present budget information with restrained, precise wording. Note that the project is forecasting a modest overspend and explain the drivers clearly. Make the distinction between current spend and forecast position. Mention whether the variance is within delegated tolerance or requires formal approval.

## Slide 6
秒搭 · Slide 5
Top Risks and Issues
Risk: delayed business sign-off could affect UAT start
Risk: third-party interface readiness remains uncertain
Issue: two high-priority defects still under investigation
Issue: reporting requirements need final confirmation
Mitigation: daily triage and escalation through governance forum
Separate risks from active issues in your verbal explanation, even if both appear on one slide. For each item, cover impact, ownership, and action underway. Keep tone measured and avoid overstating confidence. Mention where escalation routes are active and where support is required from the wider stakeholder group.

## Slide 7
秒搭 · Slide 6
RAG Status by Workstream
Scope: Green
Schedule: Amber
Budget: Amber
Quality: Amber
Resourcing: Green
This slide gives a simple cross-project view often expected in UK status reporting. Explain the reason behind each rating briefly. In particular, note that governance and compliance are in place, which helps reassure stakeholders that the project remains controlled even where delivery pressure exists.

## Slide 8
秒搭 · Slide 7
Decisions Required and Next Steps
Confirm business approvers for UAT by end of week
Approve forecast budget variance or reduce scope
Escalate third-party dependency through sponsor channel
Close open defects before readiness review
Recommendation: retain target go-live with weekly checkpoint
Close with clear actions and decisions rather than a passive summary. Make explicit what is needed from sponsors, business leads, and delivery teams. End on a practical recommendation: continue towards the target date, but maintain close weekly review and be prepared to re-baseline if the current risks are not reduced in the next reporting cycle.